|  |  |  |
| --- | --- | --- |
| **SUBMITTED TO:**  Kris Riddle | **CLIENT NAME:**  Bob Newhart / Mary Newhart | **AGREEMENT DATE**:  May 24, 2024 |
| **CHANGE ORDER DATE**:  June 4, 2024 |
| **CHANGE ORDER NO.**  1 |
| **PROJECT ADDRESS:**  4286 Country Pine Ave., Long Beach, CA 90807 | | |
| **CLIENT PHONE:**  (949) 555-1212 / | **CLIENT EMAIL:**  bnewhart@funn.com / mnewhart@me.com | |

|  |  |  |
| --- | --- | --- |
| **Description of Changes to Current Design Services/Scope of Work**  **Covered by *this* Change Order** | **No. of Hours (+/-)** | **Amount +/- to Existing Price** |
| Client wants to add upstairs office to current Project | 7 | $ 1,050 |
| Rosemary Road will pick up new chandelier from Los Angeles distributor | 2 | $ 300 |
| Visit flooring store with Client | 1 | $ 150 |

**Existing Contract Price: $ 60,750**

**New Contract Price: $ 71,100**

|  |
| --- |
| **Misc. Notes Regarding Effect this Change Order Could Have on the Project (other than price)** |
|  |

|  |  |
| --- | --- |
| **ROSEMARY ROAD INTERIORS LLC**  By:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  Kris Riddle, a Managing Member | **BOB NEWHART**  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  Signature  **MARY NEWHART**  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  Signature |